## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #2 | 10
Random Time Generation | 1 | Abrar | completed | 4 | 0.5 | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Update Address toString to include time | 0.5 | Abrar | completed | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PriorityQueue compareTo using time | 0.5 | Mohammed | completed | 3 | 0 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0
Route Length and Route for Truck Simulation | 4 | Riley | completed | 8 | 0 | 0 | 0.1 | 1 | 8 | 4 | 1 | 5 | 0 | 0
Truck Simulation | 3 | Willy | completed | 4 | 0 | 0.08333 | 0.08333 | 0 | 0 | 0.5 | 0.31 | 0 | 1 | 2
Update Requirements | 0.5 | Willy | completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
UML Diagram | 0.5 | Riley | completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
User Story #3 | 12
Main Class | 3 | Mohammed
Truck, Direction, Function, and Command Classes | 3 | Abrar
Order and Address classes | 1 | Abrar
Routes | 4 | Willy |  | 4
Update Requirements | 0.5 | Willy |  | 0.25
UML Diagram | 0.5 | Mohammed
User Story #4 | 0
User Story #5 | 0
User Story #6 | 0
TOTAL |  |  |  | 27.25 | 1.5 | 3.5833 | 3.1833 | 2.5 | 8 | 5.5 | 2.31 | 6 | 1 | 6 | 0

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0