## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #3 | 12
Main Class | 3 | Mohammed
Truck, Direction, Function, and Command Classes | 3 | Abrar | completed | 3 | 0 | 0.5 | 1 | 0.5 | 0.5 | 0.5
Order and Address classes | 1 | Abrar | completed | 1 | DAY 1: 0; DAY 2: 0.5; DAY 3: 0.5; DAY 4: 0.25
Routes | 4 | Willy |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3.5
Update Requirements | 0.5 | Willy |  | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
UML Diagram | 0.5 | Mohammed
Updating GUI | 1 | Willy |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5
User Story #2 | 10
Random Time Generation | 1 | Abrar | completed | 4 | 0.5 | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Update Address toString to include time | 0.5 | Abrar | completed | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PriorityQueue compareTo using time | 0.5 | Mohammed | completed | 3 | 0 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0
Route Length and Route for Truck Simulation | 4 | Riley | completed | 8 | 0 | 0 | 0.1 | 1 | 8 | 4 | 1 | 5 | 0 | 0
Truck Simulation | 3 | Willy | completed | 4 | 0 | 0.08333 | 0.08333 | 0 | 0 | 0.5 | 0.31 | 0 | 1 | 2
Update Requirements | 0.5 | Willy | completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
UML Diagram | 0.5 | Riley | completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
User Story #4 | 0
User Story #5 | 0
User Story #6 | 0
TOTAL |  |  |  | 34.75 | 1.5 | 4.5833 | 4.6833 | 3.25 | 8.5 | 6.5 | 2.31 | 6 | 2 | 10.25 | 0

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0